## WBS
WBS Code | Task Name | Description | Owner(s) | Start Day | End Day | Dependencies | Owner Role | Planned Hours | Phase
1.1 | determine jobs |  | All
2.1 | fill out team selection form and submit |  | Connor |  |  |  | TL | 0.5
3.1 | make github |  | Fareen |  |  |  | PM | 0.5
3.2 | decide what model to use |  | All |  |  |  | All | 0.5
4.1 | requirements |  | All |  |  |  | All | 2
4.2 | personas |  | All |  |  |  | All | 2
4.3 | use cases |  | All |  |  |  | All | 2
4.4 | search for platform to create app on |  | Katarina |  |  |  | QM | 1
5.1 | set up meeting with peer reviewer |  | Sydney |  |  |  | SM | 1
5.2 | put together review package materials |  | Sydney |  |  |  | SM | 3
5.3 | email package to professor |  | Connor |  |  |  | TL | 0.5
5.4 | peer evaluations |  | All |  |  |  | All | 1
6.1 | create high level design doc |  | Sydney

## RACI Cycle 1
WBS Code | Task Name | Team Leader | PM | Dev Manager | Quality Manager | Support Manager
1 | Initiation & Planning | A | R | C | C | C
1.1 | Team Formation and jobs | A | R | C | C | C
2.1 | submit team slection form | A | C | C | C | R
3.1 | make github | A | R | I | I | I
4.1 | requirements | A | R | C | C | C
4.2 | personas | A | R | C | C | C
4.3 | use cases | A | R | C | C | C
4.4 | search for platform | A | I | I | R | I
5.1 | set up meeting with peer reviewer | C | A | I | I | R
5.2 | put together package materials | C | A | I | I | R
5.3 | email package to professor | R+A | I | I | I | I
5.4 | peer evaluations | R | R | R | R | R